## tasks updated 1017
|  |  |  | 1- 4 months |  |  |  |  | 5-14 months | [8 empty] | 15-17 months |  |  | 18 | 19 - 20 months |  | 0
Approved by SeVEDS and RED Committees. CEDS consultant attendnace in red. | 2017-02-17 | 2017-03-17 | 2017-04-17 | 2017-11-17 | 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18 | 2018-11-18 | 2018-12-18 | 2019-01-19 | 2019-02-19 | 2017-03-19 | 2017-04-19 | 2017-05-19 | 2017-06-19 | 2017-07-19
Funding secured |  |  |  | 2017-11-01
CEDS RFP committee approved |  |  |  | 2017-11-16
CEDS RFP developed & noticed |  |  |  |  | 2017-12-21
CEDS Contractor Interviews week | [6 empty] | 2018-02-26
CEDS RFP contractor approved | [7 empty] | 2017-03-15
CEDS contractor process | [8 empty] | 2017-04-01
CEDS Committee Meets (SeVEDS/RED) | [5 empty] | 2017-01-22 |  |  | 2017-04-09 | 2017-05-30 | 2017-06-07 |  |  | 2018-09-13 | 2018-10-18 | 2018-11-13 | 2018-12-04 |  |  |  | 2019-04-11 | 2017-05-30
PUBLIC MEETING SERIES: (5 public meetings) Regional Asset Mapping weeks | [10 empty] | 2017-06-04
PUBLIC MEETING SERIES: (5 meetings) Regional data presentations weeks | [13 empty] | 2018-09-10
CEDS goals dev & approved | [13 empty] | 2018-09-13
PUBLIC MEETING SERIES: (5 meetings) goal discussions weeks | [14 empty] | 2018-10-15
CEDS action plan approved | [15 empty] | 2018-11-13
PUBLIC MEETING (Single mtg): Draft CEDS hearing | [16 empty] | 2018-12-04
CEDS Projects solicited | [16 empty] | 2018-12-04
Vital Projects determined | [20 empty] | 2019-04-04
CEDS Committee approves to EDA | [20 empty] | 2019-04-11
CEDS submitted to EDA for approval | [20 empty] | 2019-04-11
CEDS revisions received from EDA , edits made and resubmitted | [21 empty] | 2019-05-11
CEDS approved by EDA | [23 empty] | 2019-07-11
Southern Vermont Summit | [9 empty] | 2017-05-30 | [11 empty] | 2017-05-30
Note on I9: Sarah Lang: Start earlier?
Note on A11: Sarah Lang: Schedule CEDS committee meetings during this time?

## RFP Committee 1017
| 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18
RFP issue date: | 2017-12-21
Deadline for proposals: |  | 2018-01-26
Review by RFP Comm: |  |  | 2018-02-12
Consultant Interviews: |  |  | 2017-02-26
Consultant Selection: |  |  |  | 2017-03-15
Start Date for consultant: |  |  |  |  | 2017-04-01

## asana
CEDS Process
CEDS committee nominated
CEDS committee selected
CEDS timeline approved
Funding secured
CEDS RFP committee approved
CEDS RFP developed
CEDS RFP revisions
CEDS RFP approved
CEDS RFP noticed
CEDS RFP submissions reviewed
CEDS RFP contractor approved
CEDS contractor process
Regional data presentations
CEDS goals approved
Regional goal discussions
CEDS action plan approved
Draft CEDS hearing
CEDS Projects solicited
Vital Projects determined
CEDS Committee approves to EDA
CEDS submitted to EDA for approval
CEDS revisions received from EDA
CEDS approved by EDA

## tasks
|  |  |  | 1- 4 months |  |  |  | 5-12 months | [7 empty] | 13-15 months |  |  | 16 | 17-18 months |  | 19 months
estimated | 2017-02-17 | 2017-03-17 | 2017-04-17 | 2017-10-17 | 2017-11-17 | 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18 | 2018-11-18 | 2018-12-18 | 2019-01-19 | 2019-02-19 | 2017-01-19 | 2017-02-19 | 2017-03-19 | 2017-04-19 | 2017-05-19 | 2017-06-19 | 2017-07-19
Funding secured
CEDS RFP committee approved
CEDS RFP developed & noticed
CEDS RFP contractor approved
CEDS contractor process
Regional data presentations
CEDS goals dev & approved
Regional goal discussions
CEDS action plan approved
Draft CEDS hearing
CEDS Projects solicited
Vital Projects determined
CEDS Committee approves to EDA
CEDS submitted to EDA for approval
CEDS revisions received from EDA
CEDS approved by EDA

## scope
|  |  |  | Advance |  |  |  | 1- 4 months |  |  |  | 5-12 months | [7 empty] | 13-15 months |  |  | 16 | 17-18 months |  | 19 months
estimated | 2017-02-17 | 2017-03-17 | 2017-04-17 | 2017-06-17 | 2017-07-17 | 2017-08-17 | 2017-09-17 | 2017-10-17 | 2017-11-17 | 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18 | 2018-11-18 | 2018-12-18 | 2019-01-19 | 2019-02-19 | 2017-01-19 | 2017-02-19 | 2017-03-19 | 2017-04-19 | 2017-05-19
META COLLABORATIVE FRAMEWORK - Pre-approved Implementation plans for each “bucket” with milestones & Roles outlined
· LEAD – Project Management Team
· Milestones – Checkins. Weekly Monday call, monthly meeting
PREGAME – INTERNAL GROUNDING with boards ‘where are we’ – what do we know, what can we do better? Ground boards in data, give them talking points>>
· LEAD - Consultant to leverage staff and boards with shared understanding and materials to deploy into the communities through events & PR
· Milestones – Training & presentation development complete within 90 days of Funding
|  |  |  | Advance |  |  |  | 1- 4 months |  |  |  | 5-12 months | [7 empty] | 13-15 months |  |  | 16 | 17-18 months |  | 19 months
estimated | 2017-02-17 | 2017-03-17 | 2017-04-17 | 2017-06-17 | 2017-07-17 | 2017-08-17 | 2017-09-17 | 2017-10-17 | 2017-11-17 | 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18 | 2018-11-18 | 2018-12-18 | 2019-01-19 | 2019-02-19 | 2017-01-19 | 2017-02-19 | 2017-03-19 | 2017-04-19 | 2017-05-19
PUBLIC KICKOFF – Major event(s) to announce CEDS process and invite participation
· LEAD- Consultant present & presents the community leadership to the region
· Milestones – Event complete within 60 days of Funding
PR Strategy and Actions
· LEAD - Laura design, JC / Sarah implement
· Milestones –PR content and actions around every event and product outlined here throughout entire CEDS process
|  |  |  | Advance |  |  |  | 1- 4 months |  |  |  | 5-12 months | [7 empty] | 13-15 months |  |  | 16 | 17-18 months |  | 19 months
estimated | 2017-02-17 | 2017-03-17 | 2017-04-17 | 2017-06-17 | 2017-07-17 | 2017-08-17 | 2017-09-17 | 2017-10-17 | 2017-11-17 | 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18 | 2018-11-18 | 2018-12-18 | 2019-01-19 | 2019-02-19 | 2017-01-19 | 2017-02-19 | 2017-03-19 | 2017-04-19 | 2017-05-19
PUBLIC EVENTS –- Multiple geographic locations in each county: (1) data discussions (2)SWOT (3) strategy sessions (3 events x 2/3 locations x 2 county = 15 total).
· LEAD – Board leaders present and facilitate
· LEAD - Logistics management – Sarah / SVEP
· Milestones – 15 events in 2 counties completed between 3 & 9 months post funding
FOCUS GROUPS - like housing, sectors, YPs with “leaders” /experts
· LEAD – Project Management Team Design
· Milestones – completed between 6 & 9 months post funding
INTERNAL STRATEGIES DEVELOPMENT with boards
· LEAD on Development of measurable goals & objectives - Consultant
· LEAD on Data research & production – Staff (Jonathan), with some Consultant
· LEAD on findings from events and focus groups – Staff (Laura / Sarah)
· Milestones – Initiate within 30 days of Public Events Conclusion (within 9-12 months)
|  |  |  | Advance |  |  |  | 1- 4 months |  |  |  | 5-12 months | [7 empty] | 13-15 months |  |  | 16 | 17-18 months |  | 19 months
estimated | 2017-02-17 | 2017-03-17 | 2017-04-17 | 2017-06-17 | 2017-07-17 | 2017-08-17 | 2017-09-17 | 2017-10-17 | 2017-11-17 | 2017-12-17 | 2018-01-18 | 2018-02-18 | 2018-03-18 | 2018-04-18 | 2018-05-18 | 2018-06-18 | 2018-07-18 | 2018-08-18 | 2018-09-18 | 2018-10-18 | 2018-11-18 | 2018-12-18 | 2019-01-19 | 2019-02-19 | 2017-01-19 | 2017-02-19 | 2017-03-19 | 2017-04-19 | 2017-05-19
BIG REGIONAL MEETING CEDS PRODUCTION & LAUNCH with final document / presentation –
· LEAD - Consultant
· Milestones – Complete within 12-15 months of funding, publication within 15-18 mo.