## Quick Gantt
Quick Gantt Chart using Excel | [34 empty] | Prepared by Chandoo.org
Project Start Date | 2019-06-01 | [14 empty] | Show help | [8 empty] | Type 1 whenever an activity happens on a date
 | time axis 2019-06-01 to 2019-11-14
Activity | Duration | 2019-06-01 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14
App Review | 4 | bar: 2019-06-01 to 2019-06-05
Project Summary | 5 | bar: 2019-06-04 to 2019-06-10
Board Review | 1 | bar: 2019-06-07 to 2019-06-14
Matching Funds ID | 11 | bar: 2019-06-07 to 2019-06-21
App Narrative draft 1 | 10 | bar: 2019-06-17 to 2019-06-28
Budget draft 1 | 9 | bar: 2019-06-18 to 2019-06-28
Form A | 1 | bar: 2019-06-18
Form B | 1 | bar: 2019-06-18
Form C | 1 | bar: 2019-06-18
Attachment A | 1 | bar: 2019-06-19
Attachment B | 1 | bar: 2019-06-19
Final Requirements review | 5 | bar: 2019-06-24 to 2019-06-28
Budget Finalized | 10 | bar: 2019-06-24 to 2019-07-05
App Narrative final | 7 | bar: 2019-07-01 to 2019-07-09
Addl documentation | 9 | bar: 2019-07-02 to 2019-07-12
Letter of Support 1 | 14 | bar: 2019-06-17 to 2019-07-19
Letter of Support 2 | 14 | bar: 2019-06-17 to 2019-07-19
misc | 1 | bar: 2019-06-24
misc | 1 | bar: 2019-06-24
Application Filed | 8 | bar: 2019-07-23 to 2019-08-01
Get Project Management Template Pack 4
Wantmore?
Instructions:
To add more activities:
1. Select Activity 20 and all the date columns.
2. Drag down to add more activities.
To add more dates:
1. Select the last date column
2. Drag side ways to add more dates.
To show Plan by week instead of day:
1. Select cell E5
2. Write =D5+7
3. Press enter
4. Select E5
5. Drag sideways until all date formulas are over-written.
Go back
Note on C3: Enter start date here